## UPGro Logical Framework
PROGRAMME NAME: |  | UPGro - Unlocking the Potential of Groundwater for the Poor
IMPACT |  | Indicator | Baseline | Progress | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target | Assumptions
|  |  | -2014 |  |  |  |  | -2019
Sustainably managed groundwater resources support increased water security for poor people in Sub-Saharan Africa | IM.1 | National Policy influence: Number of new countries with national policies that integrate groundwater use and management across water for people, food and environment. | to be determined | too early | to be determined | to be determined | to be determined | Higher than in 2014 | There is awareness, motivation and capacity of decision makers to actively take the UPGro evidence and use it when making decisions. Data on groundwater use will improve during the course of the programme to better measure tap water dependence on groundwater.
| IM.2 | International policy influence: Number of new key international publications (e.g. GLAAS, JMP, UN Development Reports) that incorporate groundwater use and management for the poor in Africa. | to be determined | too early | to be determined | to be determined | to be determined | Higher than in 2014
| IM.3 | Improved water security [indicator under discussion]: Proportion of the African population that uses groundwater as their main source of drinking water (disaggregated by protected/non protected; borehole/hand dug well/spring and income quintile [where data is available]. | to be determined | too early | to be determined | to be determined | to be determined | Higher than in 2014
Note: Impact indicators need an explicitly funded study .
OUTCOME |  | Indicator | Baseline | Progress | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target | Assumptions
|  |  | -2014 |  |  |  |  | (2019+)
Use of robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa | O.1 | Use of evidence by other researchers: Citation of UPGro research in briefing papers, working papers and conference proceedings and peer-reviewed articles and book chapters. | 0 | too early | L: 5 M:10 H: 20 In total | L: 10 M:20 H: 40 In total | L: 15 M:30 H: 60 In total | L: 20 M:40 H: 80 In total | Water has a high profile in the Sustainable Development Goals (expected). Scientific evidence carries some weight in political decision-making (at any level). Priority of groundwater relative to other sectors is high enough for discussions to take place and decisions to be taken that can lead to the Impact being achieved. Improvements and monitoring are not destabilised by crises, corruption or other sudden political change.
| O.2 | Use of evidence by national decision-makers: Number of National Sector Performance Reports, Joint Sector Review reports or other key reports, strategies and plans that directly or indirectly reference UPGro research. | 0 | 1 | 0 | 1 | 2 | 5
| O.3 | Use of evidence by international decision-makers: Number of key international documents, such as JMP, GLAAS, UN World Water Development Report that directly or indirectly reference UPGro research. | 0 | too early | 0 | 1 | 2 | 3
| O.4 | Use of evidence influencing change: Number of stories of changes to groundwater use that have affected the poor in Sub Saharan Africa, which were influenced by UPGro or where UPGro research has influenced policy, the institutional framework, practice, groundwater monitoring and research. | 0 | too early | Poor: Policy: Inst. FW: Practice: GW Mon: Research: Combination
Output 1 |  | Indicator | Baseline | Progress (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target | Assumptions
|  |  | -2014 |  |  |  |  | (2019+)
Research contributing to sustainably managed groundwater resources for poor people in Sub-Saharan Africa of a high academic quality is generated and disseminated | 1.1 | Peer-reviewed papers: Cumulative number of peer-reviewed articles in journals, conference proceedings or book chapters. | Published: Catalysts: 2 Consortium: 0 | Submitted: Catalysts: 2 Consortium: 0 In-press: Catalysts: 2 Consortium: 0 Published: Catalysts: 7 Consortium: 0 | Published: Catalysts: 15 Consortium: 0 | Published: Catalysts: 15 Consortium: 5 | Published: Catalysts: 15 Consortium: 15 | Published: Catalysts: 15 Consortium: 25 | International databases remain funded and accessible – including the Africa Groundwater Atlas. Research papers and materials will also be available for download from non-UPGro/RWSN websites where download metrics may not be available
| 1.2 | Peer-reviewed papers (impact): Proportion of papers in High Impact Journals. |  |  | 1% | 1% | 1% | 2%
| 1.3 | Peer-reviewed papers (interdisciplinarity): Proportion of papers where the authors are from different disciplines. | 0 |  | 20% | 30% | 30% | 30%
| 1.4 | Peer-reviewed papers (African authors): Proportion of papers with lead (first or second) authors based in African institutions. | 1 |  | 1st author: 2nd author: 1st or 2nd: 20% | 30% | 30% | 30%
| 1.5 | Data: Proportion of data collected by UPGro studies uploaded to NERC and ESRC data centres. | 0 | Catalysts: 1 of 15 Consortia: 0 | L: 0% M: 0% H: 0% | L:1 0% M: 25% H: 50% | L: 25% M: 50% H: 75% | 100%
| 1.6 | Dissemination: Number of research document downloads from UPGro websites. | 1241 | 338 (UPGro) 753 (RWSN) | 500 | 1000 | 2000 | 5000
OUTPUT 2 |  | Indicator | Baseline | Progress (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target | Assumptions
-2014
UPGro early career researchers equipped with the skills to collaborate and communicate their work in the wider context of poverty and groundwater science and governance | 2.1 | International events: No of early-career researchers from each project presenting research findings at international conferences. (disaggregated by sex and nationality) | Consortium Team make-up (2015): Sex: 29% Women Nationality: 40% African Sex/Nationality: African Women: 6% |  | Sex: Women: 20% Nationality: African: 20% | Sex: Women: 25% Nationality: African: 25% | Sex: Women: 30% Nationality: African: 30% | Sex: Women: 30% Nationality: African: 40% | “Early careers” refers to researchers with ten years of academics experience or less.
| 2.2 | Training, coaching and mentoring: Number of early career UPGro researchers receiving training or systematic coaching and mentoring (disaggregated by sex, nationality). | Consortium Team make-up (2015): Sex: 29% Women Nationality: 40% African Sex/Nationality: African Women: XXX |  | Prop. of above: Sex: Women: 10% Nationality: African: 50% Sex/Nationality: African Women: XXX | Prop. of above: Sex: Women: 25% Nationality: African: 60% Sex/Nationality: African Women: XXX | Prop. of above: Sex: Women: 30% Nationality: African: 70% Sex/Nationality: African Women: XXX | Prop. of above: Sex: Women: 30% Nationality: African: 80% Sex/Nationality: African Women: XXX
| 2.3 | Knowledge sharing: Proportion of UPGro “early career researchers” that have actively participated in at least one international knowledge sharing event (disaggregated by sex and nationality). | Consortium Team make-up (2015): Sex: 29% Women Nationality: 40% African Sex/Nationality: African Women: XXX |  | 20% Prop. of above: Sex: Women: 20% Nationality: African: 50% Sex/Nationality: African Women: XXX | 40% Prop. of above: Sex: Women: 25% Nationality: African: 60% Sex/Nationality: African Women: XXX | 65% Prop. of above: Sex: Women: 25% Nationality: African: 60% Sex/Nationality: African Women: XXX | 100% Prop. of above: Sex: Women: 30% Nationality: African: 80% Sex/Nationality: African Women: XXX
OUTPUT 3 |  | Indicator | Baseline | Progress (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target | Assumptions
-2014
Targeted awareness-raising of policy-makers, practitioners and change makers on the realities and potential of groundwater for the poor in Sub Saharan Africa (SSA) | 3.1 | Involvement in research: Number of stories of SSA stakeholders involved in the development of the research plans and the testing and validation of practical tools, manuals, handbooks, guidelines and frameworks for groundwater management. | 0 | too early | L: 3 M: 5 H: 10 | L: 5 M: 7 H: 20 | L: 7 M: 10 H: 30 | L: 10 M: 15 H: 40 | Source: KB follow up with researchers at or after events; blog posts on the website
| 3.2 | Briefing materials produced: Number of policy and practice briefing materials and syntheses produced by UpGro research projects. | 15 Catalyst project + 1 overall Catalyst flyer UPGro leaflet UPGro pull-up banner | 1 Catalyst Synthesis (EN/FR) 5 Consortium summary flyers Updated leaflet UPGro folder | L: 5 M: 7 H: 10 | L: 10 M: 15 H: 20 | L: 15 M: 20 H: 35 | L: 20 M: 25 H: 30
| 3.3 | Briefing materials disseminated: Analysis of briefing materials. | 800 Catalyst flyers and 300 leaflets distributed at IAH2014 and ODI event | 1 (see cell comment) | 1 | 2 | 3 | 4
| 3.4 | UPGro events*: Number of UPGro project events with policy-makers, practitioners and change makers where research findings are presented. | Africa:/ Intl: 1 (IAH 2014) UK: 2 (Geol. Soc. / ODI) | 3 | 5 | 10 | 15 | 20
| 3.5 | Decision-making processes: UPGro projects actively involved in national (and sub-national) sector processes and events (e.g. sector reviews, planning and policy meetings). | 0 | 2 | At least 1 processes or events per project (NO=0 YES=1) | 10 At least 1 processes or events per project | At least 2 processes or events per project. | At least 2 processes or events per project
Notes: *not including Catalyst project meetings and workshops
OUTPUT 4 |  | Indicator | Baseline | Progress (2015) | Milestone 1 (2016) | Milestone 2 (2017) | Milestone 3 (2018) | Target | Assumptions
-2014
Current and potential groundwater users participate and influence the UPGro research and are presented with the findings | 4.1 | Groundwater users engaging with researchers: Number of stories where users have participated and influenced the methodology and results of the UPGro research (stories should highlight participation of women and of the poor) | 0 | too early | At least 5 from the total stories collected, 20% are about women and 20% are about the poor | At least 10 | At least 15 | At least 20
| 4.2 | Reporting of research progress and findings to water users: Cumulative number of face-to-face events and activities that give feedback on the research progress, findings and practical implications to the groundwater users that are/were the target of the research. | 0 | too early | 5 in total or at least 1 per consortium project) | 10 in total or at least 2 per consortium project | 15 or at least 3 per consortium project | 20 or at least 4 per consortium project
| 4.3 | Media coverage in UPGro countries: Number of programmes or articles on UPGro work in local media (radio, newspapers, TV). | None that we are aware of 2 articles in UK/Int. magazines | 1 (+ 4 international) | 5 | 10 | 15 | 20
Note on E13: Sean Furey: Hidden Crisis work highlighted in MWE Uganda 2014 Sector Performance Report (p.155)
Note on E23: Sean Furey: "Groundwater Safety in Peri Urban Areas"
Note on E38: Sean Furey: 200 leaflets, 150 Synthesis reports, 200 Consortium flyers, 400 UPGro/RWSN USB sticks distributed at WEDC Conference and Stockholm World Water Week
Note on E39: Sean Furey: Africa: 0 Int.ernational: 3 tockholm World Water Week, WEDC Conference, IAH Congress
Note on E40: Sean Furey: 1) Hidden Crisis work highlighted in MWE Uganda 2014 Sector Performance Report (p.155) (2) Roads for Water incorporated into Ethiopian State Gov. planning
Note on E47: In UPGro countries 1 article in Lusaka Times Internationally: 1 article in Farming Today 1 article in World Highways 1 in WaterSan Perspective blog 1 panel discussion on Guardian Development Professionals Network http://www.theguardian.com/global-development-professionals-network/2015/jul/02/water-scarcity-population-growth-live-chat

## Data Collection Framework
Annual Reporting Cycles
§ NERC bi-annual report: end January / end July
§ Financial Year: April – March
§ DFID / Log Frame report: end August
§ Programme Coordination Group (PCG) Annual Progress Report – recommend end of August to align with NERC and DFID reporting
Data Collection & Reporting
Impacts
| Indicator | Data source | Frequency of measurement | Responsibility for compilation | Reporting | Reporting | Notes
[5 empty] | (which report?) | (when reported?)
Sustainably managed groundwater resources support increased water security for poor people in Sub-Saharan Africa
IM.1 | National Policy influence: Number of new countries with national policies that integrate groundwater use and management across water for people, food and environment. | [to be determined by a meta study of government policies in SSA] | 1. Baseline 2. End of Consortium Phase 3. End of (2019) Knowledge Broker Contract (2021) | Knowledge Broker? |  |  | Likely to be from UPGro countries.
Linked to possible study to examine political framing of groundwater.
IM.2 | International policy influence: Number of new key international publications (e.g. GLAAS, JMP, UN Development Reports) that incorporate groundwater use and management for the poor in Africa | [to be determined by a meta study of government policies in SSA] | 1. Baseline 2. End of Consortium Phase 3. End of (2019) Knowledge Broker Contract (2021) | Knowledge Broker? |  |  | Likely to be from UPGro countries.
Linked to possible study to examine political framing of groundwater.
IM.3 | Improved water security: Proportion of the African population that uses groundwater as their main source of drinking water (disaggregated by protected/non protected; borehole/hand dug well/spring and income quintile [where data is available]. | JMP data (and underlying MICS and other survey data) | Whenever new data is published by the JMP (usually every 2 years) | Knowledge Broker?
Outcomes
| Indicator | Data source | Frequency of measurement | Responsibility for compilation | Reporting | Reporting | Notes
[5 empty] | (which report?) | (when reported?)
Use of robust and accessible evidence on the physical, social and economic opportunities and constraints to sustainable, long-term groundwater use by the poor in Africa
O.1 | Use of evidence by other researchers: | Journal website, conferences, Google Scholar | Annual | Knowledge Broker | DFID Log Frame | August
Citation of UPGro research in briefing papers, working papers and conference proceedings and peer-reviewed articles and book chapters.
O.2 | Use of evidence by national decision-makers: | National reports, Consortium project reports | Annual reports | PCG Coordinator | DFID Log Frame | August | Likely to be from UPGro countries.
No of National Sector Performance Reports, Joint Sector Review reports or other key reports, strategies and plans that directly or indirectly reference UPGro research.
O.3 | Use of evidence by international decision-makers: | International documents | Annual | Knowledge Broker | DFID Log Frame | August
No of key international documents, such as JMP, GLAAS, UN World Water Development Report that directly or indirectly reference UPGro research.
O.4 | Use of evidence influencing change: | PCG report, Blog/Vlog posts informal meetings | Annual | PCG Coordinator | DFID Log Frame | August | Include: narrative of materials that are co-produced/ commissioned by policy makers rather than just dissemination? Be good to get a sense of demand/ use.
| Number of stories of changes to groundwater use that have affected the poor in Sub Saharan Africa, which were influenced by UPGro or where UPGro research has influenced policy, the institutional framework, practice, groundwater monitoring and research. | [5 empty] | PCG Theme 2
Outputs
| Indicator | Data source | Frequency of measurement | Responsibility for compilation | Reporting | Reporting | Notes
[5 empty] | (which report?) | (when reported?)
OUTPUT 1: Research contributing to sustainably managed groundwater resources for poor people in Sub-Saharan Africa of a high academic quality is generated and disseminated
1.1 | Peer-reviewed papers: | PIs, journal websites, ResearchGate | Quarterly (for RWSN newsletter) + ongoing updating of UPGro website | Knowledge Broker | DFID Log Frame report | Jan, Jul, Aug
| Cumulative number of peer-reviewed articles in journals, conference proceedings or book chapters. |  |  |  | NERC report
1.2 | Peer-reviewed papers (impact): | PIs, journal websites, ResearchGate | Quarterly (for RWSN newsletter) + ongoing updating of UPGro website | Knowledge Broker | DFID Log Frame report | Jan, Jul, Aug | PCG Theme 1
| Proportion of papers in High Impact Journals. |  |  |  | NERC report
1.3 | Peer-reviewed papers (interdisciplinarity): | PIs, journal websites, ResearchGate | Quarterly (for RWSN newsletter) + ongoing updating of UPGro website | Knowledge Broker | DFID Log Frame report | Jan, Jul, Aug
| Proportion of papers where the authors are from different disciplines. |  |  |  | NERC report
1.4 | Peer-reviewed papers (African authors): | PIs, journal websites, ResearchGate | Quarterly (for RWSN newsletter) + ongoing updating of UPGro website | Knowledge Broker | DFID Log Frame report | Jan, Jul, Aug
| Proportion of papers with lead (1st or 2nd) authors based in African institutions.. |  |  |  | NERC report
1.5 | Data: | PCG report | Annual | PCG Coordinator | DFID Log Frame report | Jan, Jul, Aug | PCG Theme 4
| Proportion of data collected by UPGro studies uploaded to NERC and ESRC data centres. | NERC Data Centre |  |  | NERC report
1.6 | Dissemination: | UPGro and Consortium project website | Annual | PCG Coordinator | DFID Log Frame report | Jan, Jul, Aug | See also 3.3
| Number of research document downloads from UPGro websites. |  |  |  | NERC report
OUTPUT 2: UPGro early career researchers equipped with the skills to collaborate and communicate their work in the wider context of poverty and groundwater science and governance
2.1 | International events: | PCG report | Annual | PCG Coordinator | DFID Log Frame report | August | Needs research experience year’s data for researchers. Capture PhD & non-PhD.
| No of early-career researchers from each project presenting research findings at international conferences. (disaggregated by sex and nationality) | [5 empty] | PCG Theme 2
2.2 | Training, coaching and mentoring: | PCG report | Annual | PCG Coordinator | DFID Log Frame report | August | PCG Theme 3
Number of early career UPGro researchers receiving training or systematic coaching and mentoring (disaggregated by sex, nationality).
2.3 | Programme integration: | PCG report | Annual | PCG Coordinator | DFID Log Frame report | August | PCG Theme 1
Number of UPGro workshops, and stakeholder events supported by UPGro integration and catalyst grant funding-
2.4 | Knowledge sharing: | PCG report | Annual | PCG Coordinator | DFID Log Frame report | August | PCG Theme 2
Proportion of UPGro “early career researchers” that have actively participated in at least one international knowledge sharing event (disaggregated by sex and nationality).
OUTPUT 3: Targeted awareness-raising of policy-makers, practitioners and change makers on the realities and potential of groundwater for the poor in Sub Saharan Africa (SSA)
3.1 | Involvement in research: | Blog/Vlog posts newsletter, informal meetings | Annual | PCG Coordinator | DFID Log Frame report | August | PCG Theme 2
Number of stories of SSA stakeholders involved in the development of the research plans and the testing and validation of practical tools, manuals, handbooks, guidelines and frameworks for groundwater management.
3.2 | Briefing materials produced: Number of policy and practice briefing materials and syntheses produced by UpGro research projects. | Briefing notes, leaflets, infographics, summaries and synthesis | Bi-annual | Knowledge Broker | DFID Log Frame report | Jan, Jul, Aug | PCG Theme 2
[5 empty] | NERC report |  | Need to assure quality & not overwhelm audience.
3.3 | Briefing materials disseminated: | Printing orders, records from events, statistics from UPGro and Consortium websites | Bi-annual | Knowledge Broker | DFID Log Frame report | Jan, Jul, Aug | PCG Theme 2
| Analysis of briefing materials. |  |  |  | NERC report |  | Understand which products are being downloaded.
3.4 | UPGro events*: | Blog/Vlog posts newsletters, project reports | Annual | PCG Coordinator & Knowledge Broker | DFID Log Frame report | Jan, Jul, Aug | PCG Theme 2
| Number of UPGro project events with policy-makers, practitioners and change makers where research findings are presented. |  |  |  | NERC report |  | Milestones for total no. Disaggregate reporting into Intl., Africa & UK.
3.5 | Decision-making processes: | Blog/Vlog posts newsletters, project reports | Annual | PCG Coordinator & Knowledge Broker | DFID Log Frame report | Jan, Jul, Aug | PCG Theme 2
| UPGro projects actively involved in national (and sub-national) sector processes and events (e.g. sector reviews, planning and policy meetings). |  |  |  | NERC report
OUTPUT 4: Current and potential groundwater users participate and influence the UPGro research and are presented with the findings
4.1 | Groundwater users engaging with researchers: | Blog/Vlog posts newsletters, project reports | Annual | Knowledge Broker
Number of stories where users have participated and influenced the methodology and results of the UPGro research (stories should highlight participation of women and of the poor)
4.2 | Reporting of research progress and findings to water users: | Blog/Vlog posts newsletters, project reports | Annual | Knowledge Broker | DFID Log Frame report | August
Cumulative number of face-to-face events and activities that give feedback on the research progress, findings and practical implications to the groundwater users that are/were the target of the research.
4.3 | Media coverage in UPGro countries: | Blog/Vlog posts newsletters, project reports | Annual | Knowledge Broker | DFID Log Frame report | August
Number of programmes or articles on UPGro work in local media (radio, newspapers, TV).
OUTPUT 5: Effective management of the research programme & programme integration
5.1 | Catalyst research that meets the quality standards set by the programme awarded and completed. | PEB | Annual? | NERC
5.2 | Consortium research that meets the quality standards set by the programme awarded and completed. | PEB | Annual? | NERC |  |  | Possible link to mid-term review
5.3 | Knowledge Broker annual work plan confirmed, annual report submitted according to quality standards of programme, and activity funding is awarded. | Knowledge Broker work plan | Annual | PEB
5.4 | Integration & capacity strengthening events: | Webinar recordings, event reports, newsletter | Annual | PCG Coordinator | DFID Log Frame report | August
Number of programme integration webinars, workshops and other events.
5.5 | Integration reporting: | PCG report | Annual | PCG Coordinator | DFID Log Frame report | August
Annual report submitted according to quality standards of programme.

## Papers
Year | Status | Project | Project Type | Paper | Authors | Journal | Journal Impact Factor | Downloads | Online Views | Citations | African (1st-2nd author) | inter-disciplinarity | UPGro Direct or Indirect?
[8 empty] | (07.09.15) | (07.09.15) | (07.09.15)
2014 | Published | Fluoride Mapping | Catalyst | Chronic Alcohol Consumption and the Development of Skeletal Fluorosis in a Fluoride Endemic Area of the Ethiopian Rift Valley | Tekle-Haimanot, R. and Haile, G. | Journal of Water Resource and Protection, 6, 149-155. doi: 10.4236/jwarp.2014.62020. | 0.81 | 960 | 1925 | 1 | Yes | No | Direct
2014 | Published | Roads for Water | Catalyst | Roads for water: the unused potential | Garcia-Landarte Puertas D. , K. Woldearegay, L. Mehta, M. Van Beusekom, M. Agujetas Peréz and F. Van Steenbergen | Waterlines, Vol 33, No. 2 http://dx.doi.org/10.3362/1756-3488.2014.013, ISSN: 0262-8104 (print) 1756-3488 (online) | n/a | not available | not available | 1 | Yes | Yes | Direct
2014 |  | TOTAL: | 2 |  |  |  |  | 960 | 1925 | 2 | 100% | 50%
2015 | Published | ARIGA | Catalyst | Fresh groundwater for Wajir—ex-ante assessment of uncertain benefits for multiple stakeholders in a water supply project in Northern Kenya | Luedeling E, Oord AL, Kiteme B, Ogalleh S, Malesu M, Shepherd KD and De Leeuw J | Front. Environ. Sci. 3:16 doi: 10.3389/fenvs.2015.00016 | n/a | 146 | 1377 | 0 | Yes | No | Direct
2015 | Published | Peri-Urban Groundwater Safety | Catalyst | Patterns of domestic groundwater consumption in Kisumu, Kenya: a cross-sectional study | Okotto, L., Okotto-Okotto, J., Price, Heather, Pedley, S. and Wright, Jim | Applied Geography, 58, 189-197. (doi:10.1016/j.apgeog.2015.02.009 | 2.494 | not available | not available | 0 | Yes | Yes | Direct
2015 | Published | Peri-Urban Groundwater Safety | Catalyst | A Longitudinal Study of Long-Term Change in Contamination Hazards and Shallow Well Quality in Two Neighbourhoods of Kisumu, Kenya | Okotto, L., Okotto-Okotto, J., Price, Heather, Pedley, S. and Wright, Jim | Int. J. Environ. Res. Public Health 2015, 12(4), 4275-4291; doi:10.3390/ijerph120404275 | 2.063 | 542 | 917 | 0 | Yes | Yes | Direct
2015 | Published | Mapping groundwater quality degradation beneath growing rural towns in SSA | Catalyst | Emerging contaminants in urban groundwater sources in Africa | Sorensen, J. P. R.D.J. Lapworth,D.C.W. Nkhuwa, M.E. Stuart, D.C. Gooddy,R.A. Bell, Chirwab, M. Chirwa, J. Kabika, M. Liemisa, M. Chibesa, S. Pedley | Water Research, Volume 72, 1 April 2015, Pages 51–63 doi:10.1016/j.watres.2014.08.002 | 5.323 | not available | not available | 1 | No | No | Direct
2015 | Published | Mapping groundwater quality degradation beneath growing rural towns in SSA | Catalyst | In-situ tryptophan-like fluorescence: A real-time indicator of faecal contamination in drinking water supplies | Sorensen J, D.J. Lapworth, B.P. Marchant, D.C.W. Nkhuwa, S. Pedley, M.E. Stuart, R.A. Bell, M. Chirwa, J. Kabika, M. Liemisa, M. Chibesa | Water Research, Volume 81, 15 September 2015, Pages 38–46 | 5.323 | not available | not available | 0 | No | No | Direct
2015 | Published | Mapping groundwater quality degradation beneath growing rural towns in SSA | Catalyst | Tracing enteric pathogen contamination in sub-Saharan African groundwater | D.J Lapworth, M.E. Stuart, S. Pedley, D.C.W. Nkhuwa, M Tijani | Science of The Total Environment 538:888-895 · September 2015, DOI: 10.1016/j.scitotenv.2015.08.119 | 4.1 |  |  |  | No | No | Direct
2015 | In-press | Fluoride Mapping | Catalyst | COMPARING DEFLUORIDATION AND SAFE SOURCING FOR FLUOROSIS MITIGATION IN THE ETHIOPIAN CENTRAL RIFT | Datturi, van Steenbergen, van Beusekom, Kebede | Fluoride 48(4)281-304, October-December 2015 |  |  |  |  | Yes | No | Direct
2015 | Submitted | Roads for Water | Catalyst | “Multifunctional roads: the potential effects of combined roads and water harvesting infrastructure on livelihoods and poverty in Ethiopia”, | Demenge, J., R. Alba, K. Welle , A. Addisu and K. Manjur | Journal of Infrastructure Development |  |  |  |  | No | Yes | Direct
2015 | Submitted | Hidden Crisis | Catalyst | “Functionality” of rural water services in developing countries. | Carter R C and Ross I. | Waterlines | n/a |  |  |  | No | No | Direct
2015 |  | TOTAL: | 9 |  |  |  |  | 688 | 2294 | 1 | 44.44% | 33.33%
Peer Reviewed Papers – related work by UPGro researchers not directly funded by UPGro
2014 | Published | GroFutures | Consortium | Long-term increase in diffuse groundwater recharge following expansion of rainfed cultivation in the Sahel, West Africa | Maïmouna Ibrahim, Guillaume Favreau, Bridget R. Scanlon, Jean Luc Seidel, Mathieu Le Coz, Jérôme Demarty, Bernard Cappelaere | Hydrogeology Journal | 1.712 | [5 empty] | Indirect
2014 | Published | GroFutures | Consortium | When wells runs dry | R Taylor | Nature | 42.35 | [5 empty] | Indirect
2014 | Published | Coastal Groundwater | Catalyst | Modelling the response of fresh groundwater to climate and vegetation changes in coral islands | Comte J.C., Join J.L., Banton O., Nicolini E. | Hydrogeology Journal, DOI 10.1007/s10040-014-1160-y | 1.712 | [5 empty] | Indirect
2014 | Published | Coastal Groundwater | Catalyst | Groundwater prospection in Grande Comore Island: joint contribution of geophysical methods, hydrogeological time-series analysis and groundwater modelling | Bourhane A., Comte J.C., Join J.L., Ibrahim K. | Springer book: Active Volcanoes of the Southwest Indian Ocean, Edited by Bachelery et al. | n/a | [5 empty] | Indirect
2014 |  | TOTAL
2015 | Published | Gro for Good | Consortium | Is community water management the community’s choice? Implications for water and development policy in Africa | Hope, R. | Water Policy, 17: 664-678.. | [6 empty] | Indirect
2015 | Published | Gro for Good | Consortium | Pump-Priming Payments for Sustainable Water Services in Rural Africa. | Koehler, J., Thomson, P. & Hope, R. | World Development, Vol. 74, pp. 397-411, doi:10.1016/j.worlddev.2015.05.020. | [6 empty] | Indirect
2015 |  | TOTAL

## Data
Year | Status | Project | Project Type | Data | Authors | DOI
2014 | Under embargo until 31/03/2016 | Groundwater Safety in Peri-Urban Areas | Catalyst | “Sanitary risk inspections of shallow wells, boreholes and springs in Kisumu, Kenya in 2014”, | Okotto, L.,Okotto-Okotto, J.,Price, H.,Pedley, S.,Wright, J. | doi:10.5285/bc1a979b-7cc9-4c9d-9fe4-a8510cd62f8e
2014 | Under embargo until 31/03/2017 | Groundwater Safety in Peri-Urban Areas | Catalyst | “Socio-economic survey of domestic groundwater handling and use for source owners in Kisumu, Kenya in 2014”, | Okotto, L.,Okotto-Okotto, J.,Price, H.,Pedley, S.,Wright, J. | doi:10.5285/4ca855a3-752c-4492-8e26-3438652dd35c
2014 | Under embargo until 31/03/2018 | Groundwater Safety in Peri-Urban Areas | Catalyst | “Groundwater microbiology and chemistry of shallow wells, boreholes and springs in Kisumu, Kenya in 2014”, | Okotto, L.,Okotto-Okotto, J.,Price, H.,Pedley, S.,Wright, J. | doi:10.5285/4062e6d9-2e90-4775-87f1-179dea283ef1
2014 | Under embargo until 31/03/2019 | Groundwater Safety in Peri-Urban Areas | Catalyst | “Socio-economic survey of domestic groundwater handling and use for source customers in Kisumu, Kenya in 2014” | Okotto, L.,Okotto-Okotto, J.,Price, H.,Pedley, S.,Wright, J. | doi:10.5285/6f3f1d06-4e6b-435e-a770-af7549993b88

## Conferences
Presenters (Output 2.1)
Year | Status | Conference Name | Dates | Location | Papers/ Abstracts | Presentations | Posters | UPGro Stand? | UPGro Side Event? | UPGro organised? | Briefing Materials Disseminated | KB Priority | Total UPGro | African | Women | African Women | Early Career
2015 | Completed | RWSN Webinars - Late 2014 series | Oct-Dec 2014 | Online |  | 6 |  | - | - | Yes | Yes | Yes | 9 | 2 | 1 | 0 | 1
2014 | Completed | ODI special UPGro event: Groundwater, poverty and development | 2015-11-01 | London, UK |  | 10 |  | No | - | Yes | Yes | Yes | 10 | 1 | 3 | 0 | 2
2014 | Completed | 41st IAH Congress | 2014-09-01 | Marrakech, Morocco | 13 | 13 | 3 | Yes | Yes | No | Yes | Yes | 20 | 11 | 5 | 1 | 5
2015 | Completed | Tropentag | 2014-09-01 | Prague, Czech Republic | 1 | 1 |  | No | No | No | No | No | 1 | 0 | 0 | 0 | 0
2014 | Completed | 37th WEDC International Conference, | 2014-09-01 | Hanoi, Vietnam | 1 | 1 |  | No | No | No | No | No | 1 | 0 | 0 | 0 | 1
2014 | Completed | Geol. Soc. Groundwater Event with HWB-UK | 2014-06-01 | London, UK |  | 1 |  | Yes | - | No | Yes | Yes | 2 | 0 | 0 | 0 | 0
2014 |  | TOTAL: | 6 |  | 15 | 26 | 3 | 40% | 20% | 20% | 60% | 60% | 43 | 32.56% | 20.93% | 2.326% | 20.93%
2015 | Completed | WaTER Conference | 2015-09-01 | Oklahoma, USA | 1 | 1 |  | No | No | No | Yes | Yes | 1 | 0 | 1 | 0 | 0
2015 | Completed | 42nd IAH Congress | 2015-09-01 | Rome, Italy | 4 | 4 | 1 | No | No | No | No | No | 5 | 0 | 0 | 0 | 2
2015 | Completed | 1st Int. Roads Federation Regional Congress | 2015-09-01 | Istanbul Turkey | 1 | 1 |  | No | No | No | No | No | 1 | 0 | 0 | 0 | 0
2015 | Completed | SIWI World Water Week | 2015-08-01 | Stockholm, Sweden |  | 4 | 2 | Yes | No | No | Yes | Yes | 3 | 0 | 1 | 0 | 3
2015 | Completed | 38th WEDC International Conference, | 2015-07-01 | Loughborough, UK | 2 | 4 |  | Yes | Yes | No | Yes | Yes | 4 | 0 | 1 | 0 | 3
2015 | Completed | RWSN Webinars - Early 2015 series | Feb/Mar 2015 | Online |  | 3 |  | - | - | Yes | Yes | Yes | 4 | 2 | 1 | 1 | 1
2015 | Completed | 2015 UN Water Annual Conference | 2015-01-01 | Zaragoza, Spain |  | 3 |  | No | Yes | No | No | No | 3 | 0 | 1 | 0 | 2
2015 |  | TOTAL: | 7 |  | 7 | 19 | 3 | 33.33% | 33.33% | 16.67% | 50% | 50% | 21 | 9.524% | 23.81% | 4.762% | 52.38%
Note on G5: Sean Furey: includes 2 keynote addresses
Note on J5: Sean Furey: 3 side events - UPGro, Groundwater Atlas and GroFutures
Note on F11: Sean Furey: Keynote address
Note on J14: Sean Furey: Oxford had a session that was connected to their UPGro work
Note on J17: Sean Furey: organised by UNICEF